## Sheet1
Risk ID | Risk Description | Threat Source | Impacted Asset | Likelihood | Impact | Risk Score | Risk Level | Existing Controls / Notes | Mitigation Plan | Owner | Review Date
R001 | Employee laptop is stolen or hacked | Insider threat or physical theft | Employee device, business data | Medium (2) | High (3) | 6 | High | Endpoint protection, remote wipe, MFA | Enforce full-disk encryption, require auto-lock, and regular security awareness training | IT Manager | 2025-07-01
R002 | Unauthorized access to Shopify admin | Phishing or brute force | Shopify backend | Low (1) | High (3) | 3 | Medium | Limit admin access, strong passwords | Enforce 2FA, IP restrictions, and role-based access | Shopify Admin | 2025-07-01
R003 | Weak Google Drive sharing permissions | Insider error | Customer database, policies | Medium (2) | Medium (2) | 4 | Medium | Monthly permission reviews | Configure group-based Drive permissions, implement quarterly audits | Data Protection Officer | 2025-06-30
R004 | Phishing email leads to credential theft | External attacker | Gmail + Shopify admin | High (3) | High (3) | 9 | Critical | Phishing training, MFA | Conduct monthly phishing simulations, use email filtering tools | Security Officer | 2025-06-20
R005 | Stripe misconfiguration exposes customer data | Human error | Payment & customer info | Low (1) | Critical (4) | 4 | Medium | Role-based access, config checks | Perform weekly Stripe audits, restrict config access to senior staff | Payments Lead | 2025-07-05
R006 | Shopify app injects malicious code | Third-party vendor | Customer site, frontend | Medium (2) | High (3) | 6 | High | Vet all apps, use only trusted providers | Only allow pre-approved apps, review app permissions monthly | DevOps Lead | 2025-06-28
R007 | Employee leaves without revoking access | Internal risk | All systems: email, Stripe, Shopify | Medium (2) | Medium (2) | 4 | Medium | Offboarding checklist | Ensure offboarding process includes revoking access from all systems | HR / IT | 2025-07-03
R008 | DDoS attack takes down storefront | External attacker | Shopify store availability | Low (1) | High (3) | 3 | Medium | Shopify has built-in DDoS protection | Create incident response plan for DDoS, coordinate with Shopify support | IT Lead | 2025-07-10
R009 | Misdelivery causes chargebacks or data complaints | Logistics partner | Customer data & payment reputation | Medium (2) | Medium (2) | 4 | Medium | Use trusted courier, delivery proof | Verify addresses before shipment, enable delivery verification | Ops Manager | 2025-06-30
R010 | Gmail account gets locked or lost | Mismanagement or phishing | Company email access | Low (1) | High (3) | 3 | Medium | Use backup email, recovery codes | Set up backup admin accounts, document recovery steps | SysAdmin | 2025-06-25
R011 | Unpatched plugin vulnerability in Shopify | Third-party plugin provider | Shopify storefront, customer data | Medium (2) | High (3) | 6 | High | Regular plugin audits, auto-updates | Establish monthly plugin reviews, enforce use of trusted plugins only | Security Analyst | 2025-07-01
R012 | Misdelivery of sensitive files via email | Human error | Customer PII, partner data | Medium (2) | Medium (2) | 4 | Medium | Email DLP, double-check workflows | Implement training for safe file sharing; enable DLP alerts on email | Compliance Officer | 2025-06-15
R013 | Shopify API key exposure in GitHub repo | Developer mistake | Shopify backend, orders, customer data | High (3) | Critical (4) | 12 | Critical | Secret scanning, environment variables | Use Git hooks to prevent secrets; enforce secret scanning in CI/CD | DevOps Lead | 2025-06-20
R014 | Data loss due to accidental deletion in Google Drive | Insider error | Internal documentation, customer records | Low (1) | High (3) | 3 | Medium | File versioning, cloud backups | Enable Drive trash retention and auto-backup of key folders | IT Support | 2025-06-10
R015 | Third-party app requesting excess permissions | External app developer | Shopify admin, customer data | Medium (2) | High (3) | 6 | High | App vetting, permission reviews | Conduct quarterly app permission audits, limit app scope | Risk Manager | 2025-07-05