## Sheet1
Risk ID | Risk Description | Threat Source | Impacted Asset | Likelihood | Impact | Risk Score | Risk Level | Existing Controls / Notes
R001 | Employee laptop is stolen or hacked | Insider threat or physical theft | Employee device, business data | Medium (2) | High (3) | 6 | High | Endpoint protection, remote wipe, MFA
R002 | Unauthorized access to Shopify admin | Phishing or brute force | Shopify backend | Low (1) | High (3) | 3 | Medium | Limit admin access, strong passwords
R003 | Weak Google Drive sharing permissions | Insider error | Customer database, policies | Medium (2) | Medium (2) | 4 | Medium | Monthly permission reviews
R004 | Phishing email leads to credential theft | External attacker | Gmail + Shopify admin | High (3) | High (3) | 9 | Critical | Phishing training, MFA
R005 | Stripe misconfiguration exposes customer data | Human error | Payment & customer info | Low (1) | Critical (4) | 4 | Medium | Role-based access, config checks
R006 | Shopify app injects malicious code | Third-party vendor | Customer site, frontend | Medium (2) | High (3) | 6 | High | Vet all apps, use only trusted providers
R007 | Employee leaves without revoking access | Internal risk | All systems: email, Stripe, Shopify | Medium (2) | Medium (2) | 4 | Medium | Offboarding checklist
R008 | DDoS attack takes down storefront | External attacker | Shopify store availability | Low (1) | High (3) | 3 | Medium | Shopify has built-in DDoS protection
R009 | Misdelivery causes chargebacks or data complaints | Logistics partner | Customer data & payment reputation | Medium (2) | Medium (2) | 4 | Medium | Use trusted courier, delivery proof
R010 | Gmail account gets locked or lost | Mismanagement or phishing | Company email access | Low (1) | High (3) | 3 | Medium | Use backup email, recovery codes